## Substation
ARR FY 2022-23 (Amount in Rs Crore)
Sr. No. | BR. No. | Voltage class | Name of Substation | Circle | Transformation voltage level | Transformation Capacity (MVA) | Estimated cost (Rs. In Cr.) | Remaining Expected Cost | Capex as on Jul-21 | 2022-23 (Revised | 2022-23 (Previous) | Identification of site and status of possession of land | Status | Target year as per previous MYT | Revised Target year of commissioning | Remarks | Reason for Spillover | Scheme | Demand Note | Land Status
1 | 95.4/1504 Dt: 24.04.15 | 400 kV | 400 kV Bhachunda GIS substation (Dist. Kutch) (220/66 kV scheme is already approved) (1) 400/220 kV, 3 X 500 MVA (2) 6 Nos. of 400 kV feeder bays (3) 400 kV, 1 x 125 MVAR Reactor with bay | Anjar | 400/220 | 1500 | 154.26 | 52.91 | 101.35 | 7.2 | 0 | Acquired | Charged | 2019-20 | 2022-23 | Spillover | Associated line work pending | GEC-I | Y | Land Acquired
2 | 59.11/878 dated 08.10.09, 109.15/1815 dated 27.10.16 | 400 kV | 400 kV Pachham (Fedra) 400/220 kV, 2x500 MVA X'mers, 400 kV FB - 6, 220 kV FB - 6, 63 MVAR Bus Reactor, 220/66 kV, 2x160 MVA X'mer; 66 kV FB - 6 and 66 kV interconnection | S'nagar | 400/220 & 220/66 | 1320 | 262 | 29.94 | 232.06 | 16.3 | 0 | Land Acquired | Commissioned | 2020-21 | 2021-22 | Spillover | Project commissioned in 2020-21 but remote operation from 400KV Choraniya S/S - pending and ICT no. 3 Commissioning work pending | ND | Y | Land Acquired
3 | 59.11/878 dt 23-10-09 105.8/1731 dt 11-02-16 | 400 kV | 400/220/66 kV Bhogat GIS substation (Dist. Jamnagar) (1) 400/220 kV, 3 X 500 MVA (2) 220/66 kV, 2 X 160 MVA (3) 4 Nos. of 400 kV feeder bays (4) 400 kV, 1 x 125 MVAR Reactor with bay (5) 8 Nos. of 220 kV & 10 Nos. of 66 kV feeder bays | Jamnagar | 400/220 & 220/66 | 1820 | 210.9 | 10.01 | 200.89 | 16.56 | 0 | Land acquired | WIP | 2020-21 | 2022-23 | Spillover | Due to Covid-19 Pandemic Flooding at 400KV Bhogat Ss in year 2020 | GEC-I | Y | 2012-01-19
4 | 59.11/878 Dt.: 08.10.2009 119.6/1995 dated 01.06.2018 | 400 kV | 400/220 kV Kalavad GIS substation (Dist. Jamnagar) (1) 400/220 kV, 2 X 500 MVA (2) 8 Nos. of 400 kV feeder bays (3) 400 kV, 1 x 125 MVAR Reactor with bay | Jamnagar | 400/220 | 1000 | 154 | 123.58 | 30.42 | 23.1 | 61.79 | Land Acquired | civil work of CW/AG completed; NIT done | 2020-21 | 2024-25 | Spillover | Ongoing project of 220KV Kalawad S/S | GEC-II | Y | 2011-06-08
5 | 69.8/1073 27.11.2010 | 400 kV | 400 kV Achhalia 2x500 MVA X'mers, 400 kV FB - 6, 220 kV FB - 8, 63 MVAR Bus Reactor, 220/66 kV, 2x160 MVA X'mer; 66 kV FB - 6 and 66 kV interconnection | Bharuch | 400/220 & 220/66 | 1320 | 262 | 262 |  | 0 | 0 | Existing land | Civil work not awarded | 2020-21 | 2026-27 | Spillover | Land Issue | ND | Y | Existing
6 | 69.6/1071 dated 27.11.10 | 400 kV | 400 kV kV Prantij 400/220 kV, 2x500 MVA X'mers, 400 kV FB - 4, 220 kV FB - 4, 63 MVAR Bus Reactor, 220/66 kV s/s with 2x160 MVA X'mer; 66 kV FB - 6 and 66 kV interconnections | Himmatnagar | 400/220 & 220/66 | 1320 | 262 | 250.48 | 11.52 | 0 | 0 | Land acquired | Yet to do NIT | 2020-21 | 2024-25 | Spillover | As per system requirement | ND | Y | 2014-03-01
5 | 81.21/1279 dated 04.07.12 | 400 kV | 400 kV Shapar GIS substation (Dist. Surendranagar) (1) 400/220 kV, 3 X 500 MVA Trf with Bay (2) 220/66 kV 3 X 160 MVA Trf with bay (3) 10 Nos. of 400 kV feeder bays (4) 10 Nos. of 220 kV Line Bays (5) 400 kV, 1 x 125 MVAR Reactor with bay (6) 12 nos of 66 kV Bays |  | 400/220 & 220/66 | 1980 | 210 | 105.3 | 104.7 | 14.6395 | 31.59 | Land Acquired | WIP | 2020-21 | 2021-22 | Spillover | Due to Covid -19 | GEC-I | Y | 19/10/11 19/10/12
6 | 59.11/878 dated 08.10.09 119.6/1995 Dtd. 01.06.2018 | 400 kV | 400/220/66 kV Keshod GIS substation (Dist. Junagadh) (1) 400/220 kV, 2 X 500 MVA (2) 220/66 kV, 2 X 160 MVA (3) 6 Nos. of 400 kV feeder bays (4) 400 kV, 1 x 125 MVAR Reactor with bay (5) 8 Nos. of 220 kV & 8 Nos. of 66 kV feeder bays |  | 400/220 | 1000 | 250 | 249.92 | 0.08 | 2 | 0 | Demand Note Received | Civil work not awarded | 2021-22 | 2025-26 | NEW |  | GEC-II | Y | No
7 | 119.6/1995 Dtd. 01.06.18 | 400 kV | 400/220/66 kV Shivlakha GIS substation (Dist. Kutch) (1) 400/220 kV, 2 X 500 MVA (2) 220/66 kV, 2 X 160 MVA (3) 6 Nos. of 400 kV feeder bays (4) 400 kV, 1 x 125 MVAR Reactor with bay (5) 8 Nos. of 220 kV & 8 Nos. of 66 kV feeder bays |  | 400/220 & 220/66 | 1320 | 210.85 | 210.85 |  | 1 | 0 | Site not identified | Land proposal under process | Not Approved | 2025-26 | New |  | GEC-II | N | No
10 | 59.11/878 dated 08.10.09 | 400 kV | 400 kV Balani Vav (Pipavav) 400/220 kV, 2x500 MVA X'mers, 400 kV FB - 4, 220 kV FB - 4, 63 MVAR Bus Reactor, 220/66 kV s/s with 2x160 MVA X'mer; 66 kV FB - 6 and 66 kV interconnections |  | 400/220 & 220 /66 | 1000 | 250 | 242.62 | 7.38 | 0 | 0 | Land reference matter | Civil work not awarded | 2021-22 | 2025-26 | NEW |  | ND | Y | 2015-11-04
8 | 129.4/2138 dated 15.06.2020 | 400 kV | 400/220 kV, 500 MVA ICT at Ukai TPS - Replacement of 315 MVA ICT with 500 MVA ICT and 2nd 500 MVA ICT with Bays, Termination arrangement for 2nd ICT |  | 400/220 | 1000 | 36.02 | 35.66 | 0.36 | 10 | 28.528 | Acquired | WIP | Not Approved | 2021-22 | New |  | ND | Y | Existing
9 | 130.9/2173 dated 20.08.2020 | 400 kV | 400 kV Saykha (GIS) substation Ta. Wagra Dist. Bharuch 400/220 kV - 3x500 MVA Trf, 220/66 kV - 2x160 MVA Trf, 400 kV 1x125 MVAr bus reactor, 400 kV FB - 4 nos, 220 kV FB - 6 nos & 66 kV FB - 10 nos |  | 400/220 | 1820 | 248.81 | 248.81 |  | 6 | 0 | Site selected, Applied for land, Demand Note awaited | Land proposal under process | Not Approved | 2023-24 | New |  | ND | N | No
10 | 129.4/2138 dated 15.06.2020 | 400 kV | 400/220 kV, 500 MVA 2nd ICT at Wanakbori TPS along with bay |  | 400/220 | 500 | 19.84 | 19.84 |  | 8 | 0 | Acquired | Tender to be done | Not Approved | 2023-24 | New |  | ND | Y | Existing
11 | B.R 133.4/2218 dated 12.02.2021 | 400 kV | Upgradation of 220 kV Babarzar substation to 400 kV level (GIS) with 220/400 kV, 2x500 MVA, 4 Nos. 400 kV feeder bays, 125 MVAR Bus Reactor |  | 400/220 | 1000 | 138 | 138 |  | 5 |  | Acquired | Tender to be done | Not Approved | 2024-25 | NEW |  |  | Y | GSECL
12 | B.R 133.4/2218 dated 12.02.2021 | 400 kV | 400 kV Dholera GIS 400/220 kV 3x500 MVA Transformer 220/66 kV 2x160 MVA Transformer 1x125 MVAR 4 nos of 400 kV Bays |  | 400/220 | 1820 | 67 | 67 |  | 6.7 | 0 | Acquired | Estimate | Not Approved | 2023-24 | New |  | ND | Y | GPCL
|  | 400 kV Total |  |  |  | 19720 | 2735.68 | 2046.92 | 688.76 | 116.4995 | 121.908 | [6 empty] | ND
1 | 95.2/1502 dtd.24.06.2014 | 220 kV | 400 kV Sankhari (Veloda) substation 220/132 kV, 2x150 MVA X'mer | Palanpur | 220/132 | 300 | 15.47 | 15.47 |  | 0.5 | 12.376 | Acquired | WIP | 2018-19 | 2021-22 | Spillover | Change in Priority | ND | Y | Existing
2 | B.R.No.: 86.6/1347 Dt.: 04.02.13 | 220 kV | 220 kV Rajula (Sintex / Lunsapur ) 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 6 along with 66 kV interconnections | Amreli | 220/66 | 320 | 39.99 | 31.74 | 8.25 | 1.2 | 9.522 | Land Acquired | Awarded, Work completed | 2018-19 | 2021-22 | Spillover | Due to change in priority | ND | Y | 2017-07-04
3 | 89.5/1405 Dt.: 31.07.13 | 220 kV | 220 kV Khajod 220/66 kV GIS s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 6 along with 66 kV interconnections |  | 220/66 | 320 | 40.22 | 39.62 | 0.6 | 6.033 | 7.924 | Land Acquired | Phase-1 (AG & CW) NIT done. Phase-2 : After availability of line corridor | 2021-22 | 2023-24 | NEW |  | ND | Y | 2018-10-05
4 | 59.11/878 dated 08.10.09 119.6/1995 Dtd. 01.06.2018 | 220 kV | 220/66 kV Kalavad (1) 220/66 kV, 3x160 MVA (2) 8 Nos. of 220 kV & 6 Nos. of 66 kV feeder bays | Jamnagar | 220/66 | 480 | 110 | 13.06 | 96.94 | 10 | 0 | Land Acquired | Work Awarded, WIP | 2019-20 | 2021-22 | Spillover | Due to Covid-19 Pandemic Due damge of 220KV GIS Module during transportation, defect in supplied Bus Duct Poor response for erection work by agency | GEC-I | Y | 2011-06-08
5 | 99.10/1590 Dt: 09.02.15 | 220 kV | 220 kV Makansar 220/66 kV, 2X160 MVA ICTs | Gondal | 220/66 | 320 | 63.55 | 59.15 | 4.4 | 0 | 0 | Land Acquired | NIT to be done | 2019-20 | 2025-26 | Spillover | As per system requirement | ND | Y | 2014-01-27
5 | 89.5/1405 Dt.: 31.07.13 119.6/1995 Dt: 01.06.18 | 220 kV | 220 kV Kundiyana (Olpad) 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 10 |  | 220/66 | 320 | 40.22 | 36.09 | 4.13 | 6.033 | 0 | Land Acquired | NIT to be done | 2021-22 | 2024-25 | NEW |  | ND | Y | 2017-01-19
7 | 69.6/1071 dated 27.11.10 | 220 kV | 220 kV Samadhiyala (Bagasara) 220/66 kV, 2x160 MVA X'mer; 220 kV FB-2, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 6 and 66 kV interconnections |  | 220/66 | 320 | 25.76 | 30.11 | -4.35 | 0 | 0 | Site yet not finalized | Land proposal under process | 2021-22 | 2025-26 | NEW |  | ND | N | No
6 | 119.6/1995 Dt: 01.06.18 | 220 kV | 220 kV Metoda S/s 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-2, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 8 and 66 kV interconnections |  | 220/66 | 320 | 37.17 | 37.14 | 0.03 | 2.5 | 7.428 | Existing | Phase - I - Electrical side - Completed. For Bore well, shifting of water pipe and Pavar block removal work estimate under preparation. Phase - II - Turnkey GIS tender on website due date is 27.05.2020/29.05.2020 | 2021-22 | 2023-24 | NEW |  | ND | Y | Existing
9 | 105.8/1731 Dt: 11.02.16 | 220 kV | 220 kV Chiloda (up-gradation of 132 kV to 220 kV - GIS) 220/66 kV GIS substation with 2x160 MVA X'mer; 220 kV FB-6, 220 kV BC bay-1, PT Bays - 2 Nos. 66 kV FB – 8 220/132 kV, 2 X 150 MVA ICTs at 220kV Chiloda |  | 220/66 & 220/132 | 620 | 121.55 | 119.85 | 1.7 | 0 | 0 | Existing | Layout under preparation. Finalized after site visit. | 2021-22 | 2024-25 | NEW |  | ND | Y | Existing
10 | 69.6/1071 dated 27.11.10 Transferred to GEC-II Projects as per BR No:-119.6/1995 Dtd. 01.06.18 | 220 kV | 220 kV Talaja substation (Dist. Bhavnagar) (1) 220/66 kV, 2 X 160 MVA, (2) 6 Nos. 220 kV, 6 Nos. 66 kV feeder bays. |  | 220/66 | 320 | 39.58 | -6.01 | 45.59 | 0 | 0 | Land Acquired | WIP | 2020-21 | 2021-22 | Spillover | Line ROW contrains. WIP under police protection. | GEC-II | Y | Land Acquired
11 | 75.10/1184 dated 06-09-11 | 220 kV | 220 kV Gomta substation (Dist. Rajkot) (1) 220/66 kV, 2 X 160 MVA, (2) 6 Nos. 220 kV, 6 Nos. 66 kV feeder bays. |  | 220/66 | 320 | 36.36 | 34.51 | 1.85 | 0 | 0 | Land Acquired | NIT to ne done | 2020-21 | 2024-25 | Spillover | As per system requirement | GEC-II | Y | 2017-06-21
7 | 107.12/1772 Dt: 20.05.16 | 220 kV | 220 kV Sarigam GIS (Umagam) 220/66 kV, 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, PT Bays - 2 nos. 66 kV FB - 6 | Navsari | 220/66 | 320 | 39.58 | 36.09 | 3.49 | 23.748 | 10.827 | Existing | WIP | 2018-19 | 2023-24 | Spillover | Land Issue with Vapi GIDC. Construction permission given by Vapi GIDC on Dtd. 20.09.2021 | ND | Y | Existing
13 | 86.6/1347 Dt.: 04.02.13 130.9/2173 dated 20.08.2020 | 220 kV | 220 kV Veraval GIS 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 8 along with 66 kV interconnections |  | 220/66 | 320 | 88.27 | 88.27 | 0 | 0 | 0 | Existing | - | 2020-21 | 2024-25 | Spillover | Layout of S/S not finalised. NIT for civil and electrical works, are pending. | ND | Y | Existing
8 | 86.6/1347 Dt.: 04.02.13 | 220 kV | 220 kV Halol 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 6 along with 66 kV interconnections |  | 220/66 | 320 | 39.99 | 39.99 | 0 | 2 | 0 | Demand Note received | Yet to award | 2020-21 | 2024-25 | Spillover | GIDC has not alloted land | ND | Y | No
9 | 99.10/1590 dated 09.02.15 | 220 kV | 220 kV Maglana 220/66 kV, 2X160 MVA ICT |  | 220/66 | 320 | 40 | 28.95 | 11.05 | 6 | 5.79 | Land Acquired | WIP | 2020-21 | 2023-24 | Spillover | Change in priority due to other time bound projects like GEC-I, Radhanesda & Kishan Suryodaya Yojana etc. | ND | Y | 2015-09-19
10 | 100.8/1606 30.03.2015 | 220 kV | 220/66 kV Babara substation 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-8, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 6 220/132 kV, 2 X 150 MVA ICTs |  | 220/66 & 220/132 | 620 | 68.75 | 68.75 |  | 1.55 |  | Land Acquired | WIP |  |  | NEW |  |  | Y | Land Acquired
17 | 105.8/1731 Dt: 11.02.16 | 220 kV | 220 kV Bhat (up-gradation of 66 kV to 220 kV - GIS) 220/66 kV, 2x160 MVA X'mer; 220 kV FB-6, 220 kV BC bay-1, PT Bays - 2 nos. 66 kV FB - 8 220/132 kV, 2 X 150 MVA ICTs; 132 kV FB-4, BC bay-1, PT Bay-2 | Nadiad | 220/66 & 220/132 | 620 | 134.2 | 74 | 60.2 | 0 | 0 | Existing | - | 2020-21 | 2027-28 | Spillover | Tentative Layout Prepared. To be taken up as per load growth of Ahmedabad Urban area | ND | Y | Existing
18 | 107.12/1772 Dt: 20.05.16 | 220 kV | Upgradation of 66kV Mahuva S/S to 220kV level HGIS/GIS 220/66 kV, 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, PT Bays - 2 nos. 66 kV FB - 6 |  | 220/66 | 320 | 99.36 | 99.36 | 0 | 0 | 0 | Existing | - | Not Approved | 2027-28 | New |  | ND | Y | Existing
19 | 107.12/1772 Dt: 20.05.16 | 220 kV | Upgradation of 66kV Velanja S/S to 220kV level HGIS/GIS system 220/66 kV, 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, PT Bays - 2 nos. 66 kV FB - 6 |  | 220/66 | 320 | 99.36 | 99.36 | 0 | 0 | 0 | Existing | - | Not Approved | 2024-25 | New |  | ND | Y | Existing
20 | 107.12/1772 Dt: 20.05.16 | 220 kV | Upgradation of 132kV Ankleshwar S/S to 220kV level HGIS/GIS system 220/66 kV, 2x160 MVA X'mer; 220 kV FB-6, 220 kV BC bay-1, PT Bays - 2 nos. 66 kV FB - 8 |  | 220/66 | 320 | 143.81 | 143.81 | 0 | 0 | 0 | Existing | - | Not Approved | 2027-28 | New |  | ND | Y | Existing
21 | 107.12/1772 Dt: 20.05.16 | 220 kV | 220kV Limzer S/S 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 6 |  | 220/66 | 320 | 36.57 | 36.57 | 0 | 0 | 0 | Site yet not finalized |  | Not Approved | 2026-27 | New |  | ND | N | No
11 | 109.16.1816 Dt: 27.10.16 123.3/2049 Dtd. 22.01.19 | 220 kV | 220kV Mera S/S / (220kV MithiPaldi S/S) 220/66 kV, 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, PT Bays - 2 nos. 66 kV FB – 10 (Provision of 4 No. of 220 kV & 6 Nos. of 66 kV bays for future purpose) |  | 220/66 | 320 | 56.23 | 56.23 | 0 | 28.115 | 28.115 | Land Acquired | Electrical: LoI 12/05/2021 | Not Approved | 2022-23 | New |  | KSY | Y | Existing
12 | 109.16.1816 Dt: 27.10.16 | 220 kV | 220kV Ghodasar (Rah) S/S 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 10 |  | 220/66 | 320 | 37.03 | 37.03 | 0 | 5.5545 | 18.515 | Land Acquired | NIT to be done | Not Approved | 2023-24 | New |  | KSY | Y | 2021-06-17
24 | 114.6/1908 Dtd. 18.09.2017 | 220 kV | 220kV Khumapur (Kheradi) S/S 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 10 |  | 220/66 | 320 | 37.03 | 37.03 | 0 | 0 | 0 | Land Acquired |  | Not Approved | 2026-27 | New |  | ND | N | No
13 | 114.6/1908 Dtd. 18.09.2017 | 220 kV | 220 kV Nichi Mandal (Vankda) / Shapar (Dist. Morbi) GIS (1) 220/66 kV, 2 X 160 MVA, (2) 6 Nos. 220 kV, 6 Nos. 66 kV feeder bays. |  | 220/66 | 320 | 41.64 | 39.97 | 1.67 | 4.164 | 0 | Land Acquired | Tender to be done | Not Approved | 2024-25 | New |  | GEC-II | Y | 2020-12-07
14 | 114.6/1908 Dtd. 18.09.2017 | 220 kV | 220 kV Giyavad substation (Dist. Morbi) (1) 220/66 kV, 2 X 160 MVA, (2) 8 Nos. 220 kV, 6 Nos. 66 kV feeder bays. |  | 220/66 | 320 | 44.8 | 42.31 | 2.49 | 22.4 | 0 | Land Acquired | WIP | Not Approved | 2022-23 | New |  | GEC-II & KSY | Y | 2020-01-01
15 | 114.6/1908 Dtd. 18.09.2017 | 220 kV | 220 kV Kamlapur substation (Dist. Rajkot) (1) 220/66 kV, 2 X 160 MVA, (2) 8 Nos. 220 kV, 6 Nos. 66 kV feeder bays. |  | 220/66 | 320 | 44.8 | 30.42 | 14.38 | 22.4 | 6.084 | Land Acquired | WIP | Not Approved | 2022-23 | New |  | GEC-II | Y | 2017-10-11
16 | 114.6/1908 Dtd. 18.09.2017 | 220 kV | 132kV System at 220kV Vijapur S/S with FB & Termination from 220/132 kV ICT to 132 kV Bus and other misc civil works |  | 220/132 | 300 | 39.86 | 39.86 | 0 | 23.916 | 0 | Existing | Tender to be done | Not Approved | 2022-23 | New |  | ND | Y | Existing
29 | 114.6/1908 Dtd. 18.09.2017 | 220 kV | 220kV Sarvala S/S 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 6 |  | 220/66 | 320 | 36.57 | 36.13 | 0.44 | 0 | 0 | Land Acquired |  | Not Approved | 2026-27 | New |  | ND | Y | 2017-03-23
17 | 114.6/1908 Dtd. 18.09.2017 | 220 kV | Up gradation of 66kV Sevalia S/S to 220kV Level 220/66 kV s/s with 2X 160 MVA Transformers, 220 kV FB-4, 220 kV BC Bay-1, 220 kV TBC-1, 66 kV FB-6 |  | 220/66 | 320 | 59.8 | 49.74 | 10.06 | 35.88 | 9.948 | Land Acquired | WIP | Not Approved | 2022-23 | New |  | ND | Y | Existing
31 | 119.6/1995 Dtd. 01.06.2018 | 220 kV | 220kV Mandali S/S 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 6 |  | 220/66 | 320 | 36.57 | 36.57 | 0 | 0 | 0 | Site yet not finalized |  | Not Approved | 2026-27 | New |  | ND | N | No
18 | 119.6/1995 Dtd. 01.06.18 | 220 kV | 220 kV Dhama (1) 220/66 kV, 2 X 160 MVA, (2) 8 Nos. 220 kV, 6 Nos. 66 kV feeder bays. |  | 220/66 | 320 | 44.8 | 44.8 | 0 | 2 | 0 | Demand Note Received | Land proposal under process | Not Approved | 2025-26 | New |  | GEC-II | Y | No
19 | 123.3/2049 Dtd. 22.01.2019 | 220 kV | Upgradation of 66kV Bhildi substation to 220kV level using Hybrid Modules 220/66 kV, 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, PT Bays - 2 nos. 66 kV FB - 10 |  | 220/66 | 320 | 56.23 | 56.23 | 0 | 33.738 | 28.115 | Existing | WIP | Not Approved | 2023-24 | New |  | KSY | Y | Existing
34 | 123.3/2049 Dtd. 22.01.2019 | 220 kV | 220kV Chikada (Satwan) (Umarpada) S/S 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-6 (additional space for 4 nos. of future bays), 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 6, U/G cable termination |  | 220/66 | 220/66 | 41.64 | 41.64 | 0 | 0 | 0 | Site yet not finalized |  | Not Approved | 2026-27 | New |  | ND | N | No
35 | 123.3/2049 Dtd. 22.01.2019 | 220 kV | 220kV Padana S/S (Avana SS/ upgradation of Gandhidham-B) S/S to 220kV Level (GIS/HGIS) 220/66 kV s/s with 2x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 6 |  | 220/66 | 320 | 90.84 | 90.84 | 0 | 0 | 45.42 | Site finanlized and applied, Demand Note Pending |  | Not Approved | 2024-25 | New |  | KSY | N | No
36 | 123.3/2049 Dtd. 22.01.2019 | 220 kV | 220 kV Bhuteshawar (Avaniya) 220/66 kV s/s with 2x160 MVA ICT; 220 kV FB-6 (additional space for 4 nos. of future bays), 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 8 |  | 220/66 | 320 | 41.64 | 39.09 | 2.55 | 0 | 0 | Land Acquired |  | Not Approved | 2025-26 | New |  | ND | Y | 2021-03-18
37 | 129.4/2138 dated 15.06.2020 | 220 kV | 220/66 kV (GIS) system at Kanbha (Upgradation) 220/66 kV, 2x160 MVA X'mer; 220 kV FB-6, 220 kV BC bay-1, PT Bays - 2 nos. 66 kV FB - 8 |  | 220/66 | 320 | 100.86 | 100.86 | 0 | 0 | 0 | Site yet not finalized |  | Not Approved | 2025-26 | New |  | ND | N | No
38 | 129.4/2138 dated 15.06.2020 | 220 kV | 220/66 kV (GIS) system at Siddheshwar (Upgradation) 220/66 kV, 3x160 MVA X'mer; 220 kV FB-4, 220 kV BC bay-1, PT Bays - 2 nos. 66 kV FB - 10 |  | 220/66 | 480 | 99.83 | 99.83 | 0 | 0 | 0 | Existing |  | Not Approved | 2024-25 | New |  | ND | Y | Existing
39 | 129.4/2138 dated 15.06.2020 | 220 kV | 220 kV Balethi (AIS) 220/66 kV s/s with 2x160 MVA X'mer (2 Nos for future provision); 220 kV FB-4 (additional space for 4 nos. of future bays), 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 10 |  | 220/66 | 320 | 43.29 | 42.82 | 0.47 | 0 | 0 | Demand Note Received |  | Not Approved | 2025-26 | New |  | ND | Y | New
40 | 129.4/2138 dated 15.06.2020 | 220 kV | 220/132 kV, 2 x 100 MVA ICTs at Dhuvaran CCPP-3 with bays |  | 220/132 | 200 | 15.18 | 15.18 | 0 | 0 | 4.554 | Existing | WIP | Not Approved | 2021-22 | New |  | ND | Y | Existing
20 | 129.4/2138 dated 15.06.2020 | 220 kV | 220kV Sisrana/ Satlasana 220/66 kV s/s with 2x160 MVA ICTs (provision to be kept for additional 2 ICTs for later stage); 220 kV FB-4 (provision to be kept for additional 8 bays for later stage), 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB – 10 |  | 220/66 | 320 | 43.29 | 43.29 | 0 | 6.4935 | 21.645 | Demand Note Received | NIT to be done | Not Approved | 2023-24 | New |  | KSY | Y | No
21 | 129.4/2138 dated 15.06.2020 | 220 kV | 220 kV Bhesan (AIS) 220/66 kV s/s with 2x160 MVA X'mer (2 Nos for future provision); 220 kV FB-5 (additional space for 4 nos. of future bays), 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB – 10 |  | 220/66 | 320 | 43.29 | 43.29 | 0 | 21.645 | 21.645 | Land Acquired on 19-03-2021 | WIP | Not Approved | 2022-23 | New |  | KSY | Y | 2021-03-19
22 | 129.4/2138 dated 15.06.2020 | 220 kV | 220kV Patkhilori 220/66 kV s/s with 2x160 MVA X'mer (provision to be kept for additional 2 ICTs for later stage); 220 kV FB-4 (provision to be kept for additional 4-6 bays for later stage), 220 kV BC bay-1, 220 kV TBC - 1, 66 kV FB - 10 |  | 220/66 | 320 | 43.29 | 43.29 | 0 | 21.645 | 21.645 | Land Acquired on 03-01-2021 | WIP | Not Approved | 2022-23 | New |  | KSY | Y | 2021-01-03
44 | 129.4/2138 dated 15.06.2020 | 220 kV | 220 kV Khodu/Dudhrej |  | 220/66 | 320 | 43.29 | 43.29 | 0 | 0 | 21.645 | Site yet not finalized |  | Not Approved | 2024-25 | New |  | KSY | N | No
23 | 130.9/2173 dated 20.08.2020 | 220 kV | 220 kV Dumas (GIS) 220/66 - 3 x160 MVA Trf, 220 kV FB - 6 nos, 66 kV FB - 8 nos |  | 220/66 | 480 | 99.88 | 80.29 | 19.59 | 2 | 0 | Demand Note Received | Land proposal under process | Not Approved | 2026-27 | New |  | ND | Y | No
24 | 130.9/2173 dated 20.08.2020 & 133.4/2218 dated 12.02.2021 | 220 kV | 220 kV Babarzar (AIS) 220/66 kV 6x160 MVA Trf,220 kV FB -4, 220 kV BC Bay - 1, 220 kV TBC - 1, 220 kV 25 MVAR Bus reactor, 66 kV FB - 16 |  | 220/66 | 960 | 84.12 | 84.12 | 0 | 42.06 | 42.06 | Land Acquired (GSECL) | WIP | Not Approved | 2022-23 | New |  | KSY | Y | GSECL
25 | 130.8/2172 dated 20.08.2020 | 220 kV | 220/33 kV Dholera Pooling Substation 220/33 kV 8x125 MVA Tfr, 220 kV FB - 4, 220 kV BC Bay - 1, PT bays - 2, 33 kV Line bays - 24 |  | 220/33 | 1000 | 165.26 | 126.73 | 38.53 | 10 | 25.346 | Land Acquired (GPCL) | WIP | Not Approved | 2023-24 | New |  | ND | Y | GPCL
48 | 130.8/2172 dated 20.08.2020 | 220 kV | 220 kV Raghanesda Pooling Substation 220/33 kV 6 x125 MVA ICT 220 kV FB -2 nos BC Bay -1 PT Bays - 2 33 kV Line bays - 18 |  | 220/33 | 750 | 122.14 | 85.58 | 36.56 | 0 | 17.116 | Land Acquired (GPCL) | Commissioned | Not Approved | 2021-22 | New |  | ND | Y | 2020-07-14
26 | 75.10/1184 dated 06-09-11 Transferred to GEC-II Projects as per BR No:-119.6/1995 Dtd. 01.06.18 | 220 kV | 220 kV Kuwadiya (Khambhalia) substation (Dist. Jamnagar) (1) 220/66 kV, 2 X 160 MVA, (2) 6 Nos. 220 kV, 6 Nos. 66 kV feeder bays. |  | 220/66 | 320 | 52 | 7.17 | 44.83 | 2 | 0 | Land Acquired on 12.11.2014 | WIP | 2021-22 | 2021-22 | NEW |  | GEC-II | Y | 2014-11-12
|  | 220 kV Total |  |  |  | 18330 | 3024.96 | 2619.51 | 405.45 | 343.575 | 365.72
1 | B.R 131.11/2200 dated 28.10.2020 | 132 kV | 132 kV Supedi |  | 132/66 | 200 | 14.84 | 14.84 | 0 | 0.8 | 0 | Existing | NIT Done | Not Approved | 2021-22 | New |  | KSY | Y | Existing
|  | 132 kV Total |  |  |  | 200 | 14.84 | 14.84 | 0 | 0.8 | 0
|  |  | Total EHV |  |  | 38250 | 5775.48 | 4681.27 | 1094.21 | 460.8745 | 487.628
66 kV Substation Lump sum @ Rs 5 Crs taking 92 nos | [5 empty] | 13650 | 2275 | 2275 |  | 460 | 445
G. Total | [5 empty] | 51900 | 8050.48 | 6956.27 |  | 920.8745 | 932.628

## Line
Annexure-1
ARR 2022-23 (Transmission Lines) (Amount in Rs Crore)
Sr. No. | Br. No. | Voltage class | Name of Transmission line | Length in Ckm | Estimated cost (Rs. In Cr.) | Remaining Cost & CKM |  | Actual 2021-22 (as on Jul-21) |  | 2022-23 Revised |  | 2022-23 |  | Status of placement of construction and other contracts | Target year of commissioning as per previous MYT | Revised Target year of commissioning | Remarks | Reason for Spillover | Locations under RoW | Scheme
[6 empty] | Ckm | Cost (Rs Crs) | Ckm | Capex (Rs Crs) | Ckm | Capex (Rs Crs) | Ckm | Capex (Rs Crs)
1 | 41.22/506 dated 09.08.2007 & 62.7/949 dated 07.04.2010 | 400 kV | 400 kV Essar - Amreli line (Twin Moose) (Vadinar- Amreli) | 356.05 | 158 | 37.13 | 94.83 | 318.92 | 63.17 | 10 | 40 | 0 | 37.932 | WIP | 2017-18 | 2022-23 | Spill over | Contractual issues and RoW issues | 37 | ND
2 | 51.2/696 dated 03.01.2008 | 400 kV | 400 kV D/C Vadavi - Halvad line | 290 | 125.3 | 125.1 | 14.78 | 164.9 | 110.52 | 80 | 12.53 | 37.53 | 10 | WIP | 2018-19 | 2022-23 | Spill over | Contractual issues and RoW issues | 5 | ND | Line considered in Line length
3 | 51.2/696 dated 03.01.2008 | 400 kV | 400 kV S/C Mundra - Hadala line LILO at Halvad | 55 | 39.58 | 0 | 13.58 | 55 | 26 | 0 | 3.958 | 0 | 2.716 | WIP | 2017-18 | 2021-22 | Spill over | Line charged on 25.11.2021 |  | ND
4 | 59.11/878 dated 08.10.2009 | 400 kV | 400 kV D/C Varsana - Halvad (Quad Moose) | 237 | 312 | 172.6 | 19.33 | 64.4 | 292.67 | 10 | 23 | 51.78 | 19.33 | WIP | 2018-19 | 2023-24 | Spill over | Contractual issues and RoW issues | Stringing RoW | ND
5 | 59.11/878 dated 08.10.2009 | 400 kV | 400 kV D/C Kasor - Amreli line (Quad Moose) | 460 | 478.97 | 237.17 | 151.66 | 222.83 | 327.31 | 40 | 90.996 | 71.151 | 90.996 | WIP | 2018-19 | 2023-24 | Spill over | Contractual issues and RoW issues | 9 | ND
6 | 99.10/1590 dated 09.02.2015 | 400 kV | 400 kV D/C Wanakbori TPS - Soja | 212 | 137.1 | 29.24 | 0 | 182.76 | 137.1 | 0 | 11 | 0 | 0 | WIP | 2018-19 | 2021-22 | Spill over | RoW issues and court matters |  | ND
7 | 99.10/1590 dated 09.02.2015 | 400 kV | 400 kV D/C Soja - Zerda line (Twin moose) | 268 | 235 | 8.5 | 19.59 | 259.5 | 215.41 | 0 | 12 | 0 | 0 | WIP | 2019-20 | 2021-22 | Spill over | RoW issues and court matters | 6 | ND
8 | BR no. 95.4/1504 dated 24.06.14 (Development of Green Energy Corridor) (Revised as per BR. No. 105.8/1731 dated 11.02.16) | 400 kV | 400 kV D/C Bhachunda - Varsana line | 264 | 210 | 236 | 63.02 | 28 | 146.98 | 100 | 20 | 70.8 | 6.302 | WIP | 2020-21 | 2022-23 | Spill over | RoW issues | 20 | ND
9 | 40.19/473 dated 31.05.2007 | 400 kV | 400 kV D/C Adani - Zerda line-1 | 666 | 330 | 666 | 134.31 | 0 | 195.69 | 50 | 80.586 | 199.8 | 40.293 | WIP | 2020-21 | 2023-24 | Spill over | Contractual issues and RoW issues | Package-3 : 105 | ND
10 | 104.13/1708 dated 21.11.2015 | 400 kV | 400 kV D/C Shapar - Fedra line (twin moose ) | 200 | 168 | 200 | 91.69 | 0 | 76.31 | 150 | 21.08 | 0 | 18.338 | WIP | 2020-21 | 2022-23 | Spill over | RoW issues | 30 | ND | Line considered in Line length
11 | 104.13/1708 dated 21.11.2015 | 400 kV | 400 kV D/C Hadala - Shapar line (Twin Moose ) | 129 | 107.95 | 29 | 45.95 | 100 | 62 | 0 | 8 | 0 | 0 | WIP | 2019-20 | 2021-22 | Spill over | RoW issues |  | ND
12 | 77.3/1203 dated 16.12.2011 | 400 kV | LILO of one ckt of 400 kV D/C Halvad - Vadavi line at 400 kV Chharodi s/s (ACSR Twin Moose) | 86 | 38.08 | 79.46 | 38.08 | 6.54 | 0 | 0 | 3.808 | 23.838 | 22.848 | WIP | 2020-21 | 2022-23 | Spill over | RoW issues | 11 | ND
13 | 95.4/1504 dated 24.06.14 (Development of Green Energy Corridor) (Revised as per BR. No. 105.8/1731 dated 11.02.16) | 400 kV | 400 kV D/C Bhogat - Kalavad line | 250 | 202.5 | 120 | 51.96 | 130 | 150.54 | 60 | 20.25 | 36 | 31.176 | WIP | 2020-21 | 2022-23 | Spill over | RoW issues |  | ND | Line considered in Line length
14 | 130.8/2172 dated 20.08.2020 & 133.4/2218 dated 12.02.2021 | 400 kV | 400KV D/C FEDRA (PACHCHHAM) - DHOLERA 'AA' LINE | 66 | 69 | 52 | 5.54 | 14 | 63.46 | 0 | 5 |  |  | WIP |  | 2021-22 | NEW |  |  | ND
15 | 130.8/2172 dated 20.08.2020 & 133.4/2218 dated 12.02.2021 | 400 kV | LILO of both circuits of 400 kV D/C Fedra - Dholera AA line at Dholera Solar Park Pooling Substation. (Extension of 400 kV D/C Fedra - Dholera 'AA' line up to Dholera Solar Park Pooling Substation (400 kV M/C with AL-59 conductor) and Termination of line on 400 KV switchyard which is intially terminated at 220 KV system | 38.664 | 56.61 | 38.664 | 34.08 | 0 | 22.53 | 0 | 5 | 0 | 6.816 | WIP | Not Approved | 2021-22 | NEW |  |  | ND
16 | 59.11/878 dated 08.10.09 | 400 kV | LILO of both circuits of proposed 400 kV D/C Kasor - Amreli line at Fedra s/s | 80 | 97.06 | 80 | 97.06 | 0 | 0 | 0 | 0 | 8 | 9.706 | Yet to Award | 2020-21 | 2024-25 |  |  |  | ND
16 | 69.8/1073 dated 27.11.10 | 400 kV | LIL O of one ckt of proposed 400 kV D/C Wanakbori - Soja line at Prantij s/s | 80 | 42.32 | 80 | 42.32 | 0 | 0 | 0 | 2 | 8 | 4.232 | Survey Route Awaiting | 2020-21 | 2024-25 | Spill over | Yet to be awarded |  | Planned in TBCB and linked with Kutch RE evacuation
18 | B.R No. 119.6/1995 dated 01.06.2018 | 400 kV | 400kV D/C Kalawad - Keshod line (2 x 120 = 240Ckm) | 240 | 198 | 240 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | Keshod land not available | Not Approved | 2025-26 |  |  |  | GEC-II
19 | B.R No. 119.6/1995 dated 01.06.2018 | 400 kV | 400kV D/C Keshod - Shapar line (2 x 190 = 380Ckm) | 380 | 313.5 | 380 | 313.5 | 0 | 0 | 0 | 0 | 0 | 0 | Keshod land not available | Not Approved | 2026-27 |  |  |  | GEC-II
20 | B.R No. 119.6/1995 dated 01.06.2018 | 400 kV | 400kV D/C Bhachunda - Shivlakha line (2 x 210 = 420KM) | 420 | 346.5 | 420 | 346.5 | 0 | 0 | 0 | 0 | 0 | 0 | Shivlakha land not available | Not Approved | 2025-26 |  |  |  | GEC-II
21 | B.R No. 119.6/1995 dated 01.06.2018 | 400 kV | 400kV D/C Shapar - Chharodi line (2 x 90 = 180KM) | 180 | 148.5 | 180 | 148.5 | 0 | 0 | 0 | 0 | 18 | 14.85 | Survey letter issued on 08.04.2020 | Not Approved | 2024-25 |  |  |  | GEC-II
22 | B.R No. 119.6/1995 dated 01.06.2018 | 400 kV | 400kV D/C Shivlakha - Veloda line (2 x 245 = 490KM) | 490 | 404.25 | 490 | 404.25 | 0 | 0 | 0 | 0 | 0 | 0 | Shivlakha land not available | Not Approved | 2026-27 |  |  |  | GEC-II
17 | B.R No. 119.6/1995 dated 01.06.2018 | 400 kV | 400kV D/C Veloda - Prantij line (2 x150 = 300KM) | 300 | 247.5 | 300 | 247.5 | 0 | 0 | 0 | 2 | 0 | 0 | Estimate prepared | 2020-21 | 2025-26 | Spill over | Yet to be awarded |  | GEC-II
24 | B.R No. 119.6/1995 dated 01.06.2018 | 400 kV | LILO of one ckt of 400kV D/C Soja - Zerda line at Veloda (2 x 50 = 100Ckm) | 100 | 82.5 | 100 | 82.5 | 0 | 0 | 0 | 0 | 10 | 8.25 | Survey letter issued on 08.04.2020 | Not Approved | 2024-25 |  |  |  | GEC-II
25 | 130.9/2173 dated 20.08.2020 | 400 kV | LILO of 400 kV S/C Kosamba-Pachham line at 400 kV Saykha | 4 | 3.33 | 4 | 3.33 | 0 | 0 | 0 | 0 | 0 | 0 | Land not available | Not Approved | 2026-27 |  |  |  | ND
26 | 130.9/2173 dated 20.08.2020 | 400 kV | LILO of 400 kV S/C Kosamba-Charal line at 400 kV Saykha | 4 | 3.33 | 4 | 3.33 | 0 | 0 | 0 | 0 | 0 | 0 | Land not available | Not Approved | 2026-27 |  |  |  | ND
18 | B.R No. 119.6/1995 dated 01.06.2018 | 400 kV | LILO of 400kV S/C Chorania - Asoj line at 400kV Pachham (Fedra ) S/s (2 x 25 = 50Ckm) | 50 | 41.25 | 50 | 41.25 | 0 | 0 | 0 | 4.125 | 15 | 16.5 | Survey letter issued on 08.04.2020 | Not Approved | 2023-24 | NEW |  |  | GEC-II
28 | 69.8/1073 27.11.2010 | 400 kV | LILO of 400 kV S/C SSP - Asoj & Kasor line at Achhalia substation (2x40=80 Ckm) | 80 | 42.32 | 80 | 42.32 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
29 | 109.16/1816 dtd. 27.10.16 | 400 kV | 400 kV D/C Kosamba - Achhalia line (2X70= 140 Ckm) (conductor configuration changed from Twin Moose to Twin AL-59 vide BR. No. 109.16/1816 dtd. 27.10.16) | 140 | 83.32 | 140 | 83.32 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
30 | B.R 133.4/2218 dated 12.02.2021 | 400 kV | LILO of both circuits of 400 KV D/C Bhogat - Kalavad line at Babarzar substation | 6 | 10.76 | 6 | 10.76 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-24 |  |  |  | ND
31 | 95.2/1502 dated 24.06.14 | 400 kV | 400kV D/C Pipavav - Amreli line (2x95=190 Ckm) (Additional Budget for 20KM approved vide BR no. 95.2/1502 dated 24.06.14) (conductor configuration changed from ACSR Quad Moose to Twin AL-59 vide BR. No. 109.16/1816 dtd. 27.10.16) | 190 | 181.99 | 190 | 181.99 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
400 kV Total |  |  |  | 6321.714 | 4914.52 | 4774.864 | 3024.83 | 1546.85 | 1889.69 | 500 | 365.333 | 549.899 | 340.285 | [6 empty] | ND
1 | 51.2/696 dated 10.11.2008 62.8/950 dated 07.04.2010 | 220 kV | 220 kV D/C Gavasad - Salejda line | 194 | 63.9 | 113 | 0.47 | 81 | 63.43 | 30 | 5 | 22.6 | 0.282 | WIP | 2017-18 | 2022-23 | Spill over | Contractual issues |  | ND
2 | B.R. No. 86.6/1347 dated 04.02.13 | 220 kV | LILO of 220 kV S/C Vadavi - Chhatral line at 220 kV Santej substation | 50.66 | 13.94 | 46.93 | -1.54 | 3.73 | 15.48 | 0 | 0 | 0 | 0 | Line charged on 19.08.21 | 2017-18 | 2021-22 |  |  |  | ND
3 | BR no. 114.6/1908 dated 18.09.17 | 220 kV | 220kV D/C Vadodara(PG) – Jambuva line | 67.96 | 27.76 | 67.96 | 27.76 | 0 | 0 | 0 | 0 | 0 | 0 | Commissioned on 17/11/2020 | 2018-19 | 2020-21 |  |  |  | ND
2 | 109.16/1816 dated 27.10.2016 | 220 kV | LILO of one circuit of 220 kV D/C Jetpur - Sardargadh line at 220 kV Shapur substation | 12 | 7.14 | 5 | 1.12 | 7 | 6.02 | 0 | 0.6 | 0 | 0 | WIP | 2018-19 | 2021-22 | Spill over | RoW issues |  | Scheme Revised
3 | B.R. No. 89.5/1405 dated 31.07.13 | 220 kV | LILO of both ckt of 220 kV D/C Kawas - Nvasari(PG) line at 220 kV Khajod s/s | 20 | 2.92 | 20 | 2.92 | 0 | 0 | 0 | 0.584 | 2 | 0.292 | Survey report received | 2020-21 | 2024-25 | Spill over | Yet to be awarded |  | ND
6 | 129.4/2138 dated 15.06.2020 | 220 kV | LILO of 220 kV S/C Ichhapore – Talangpore line at proposed 220 kV Khajod substation | 7 | 3.04 | 7 | 3.04 | 0 | 0 | 0 | 0 | 0.7 | 0.304 | Survey report received | Not Approved | 2023-24 |  |  |  | ND
4 | 77.3/1203 16.12.2011 92.7/1444 12.12.2013 | 220 kV | 220 kV D/C BECL- Botad | 190 | 16.96 | 156 | 5.36 | 34 | 11.6 | 100 | 2 | 0 | 1.072 | WIP | Not Approved | 2022-23 | NEW |  |  | ND
8 | 59.11/878 08.10.2009 | 220 kV | 220kV D/C Halvad - Sadla line with AL-59 conductor | 74.4 | 31.78 | 0.4 | 14.76 | 74 | 17.02 | 0 | 0 | 0 | 0 | Line charged on 220kV on dt: 06.10.21 | Not Approved | 2021-22 |  |  |  | ND
5 | 119.6/1995 Dtd. 01.06.2018 | 220 kV | 220kV D/C Chorania - Salejada line with AL-59 conductor | 134.4 | 44.82 | 91.4 | 7.67 | 43 | 37.15 | 10 | 1.53 | 0 | 1.534 | WIP | Not Approved | 2022-23 | NEW |  |  | ND | Line considered in Line length
6 | 75.10/1184 dated 06.09.2011 | 220 kV | 220 kV D/C Bhatia - Kalavad line | 238 | 50.85 | 227 | 14.35 | 11 | 36.5 | 80 | 6 | 45.4 | 8.61 | WIP | 2017-18 | 2022-23 | Spill over | Risk purchase work yet to be awarded |  | ND
7 | B.R.No. 75.10/1184 dated 06-09-11 | 220 kV | 220 kV D/C Kalavad - Kangasiali | 112 | 50.85 | 24 | 23.85 | 88 | 27 | 0 | 6 | 0 | 4.77 | WIP | 2017-18 | 2022-23 | Spill over | Contractual issues and RoW issues | 17 | ND | Line considered in Line length
8 | 84.11/1325 dated 05.10.12 | 220 kV | 220 kV D/C Chorania - Botad line | 104 | 35 | 84 | 15.57 | 20 | 19.43 | 20 | 2 | 0 | 3.114 | WIP | 2018-19 | 2022-23 | Spill over | Contractual issues |  | ND
13 | B.R. No. 84.11/1325 dated 05.10.12 | 220 kV | LILO of one circuit of 220 kV D/C Amreli - Dhasa line at Gariyadhar | 70 | 17.02 | 70 | 17.02 | 0 | 0 | 0 | 0 | 7 | 1.702 | To review | 2021-22 | 2024-25 |  |  |  | ND
14 | 107.12/1772 dated 20.05.2016 | 220 kV | LILO of one circuit of 220 kV D/C Ukai(Thermal) - Achhalia 3 line at 220 kV Virpore | 27.08 | 21.04 | 27.08 | 9.35 | 0 | 11.69 | 0 | 0 | 0 | 0 | Commissioned on 24/12/2020 | 2018-19 | 2020-21 |  |  |  | ND
15 | 107.12/1772 dated 20.05.2016 | 220 kV | LILO of 220 kV S/C Ukai(Thermal) - Achhalia line - 2 at 220 kV Virpore | 42.58 | 21.04 | 42.58 | 1.38 |  | 19.66 | 0 | 0 | 0 | 0 | Commissioned on 08/02/2021 | 2018-19 | 2020-21 |  |  |  | ND
16 | 107.12/1772 dated 20.05.2016 | 220 kV | 220 kV D/C Virpore - Chikhli line | 120 | 42.09 | 120 | 42.01 |  | 0.08 | 0 | 0 | 12 | 4.201 | Resurvey if survey report is old by 2 years | 2019-20 | 2024-25 |  |  |  | ND
17 | 107.12/1772 dated 20.05.2016 | 220 kV | LILO of both ckts of 220kV D/C Navsari - Nasik line at 220kV Limzer S/s (4 x 30 =120Ckm) | 120 | 47.61 | 120 | 47.61 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
18 | 107.12/1772 dated 20.05.2016 | 220 kV | LILO of both ckts of 220kV D/C Kawas - Haldarwa at Ankleshwar by using existing RoW of 132kV D/C Ankleshwar - Bharuch line (4 x 10 =40Ckm) | 40 | 48.76 | 40 | 48.76 |  | 0 | 0 | 0 | 0 | 0 | Survey done but compliance of query pending | Not Approved | 2027-28 |  |  |  | ND
9 | 107.12/1772 dated 20.05.2016 | 220 kV | LILO of 220kV S/C GSEG - Kim and S/C GSEG - Mora - Kim at Velanja (4 x 10=40Ckm) | 7.04 | 15.87 | 7.04 | 13.79 | 0 | 2.08 | 0 | 2.76 | 0 | 2.758 | WIP | Not Approved | 2021-22 | NEW |  |  | ND
20 | 107.12/1772 dated 20.05.2016 | 220 kV | LILO of both circuits of 220 kV D/C Mota - Chikhli (Ambheta) line at Mahuva | 40 | 15.87 | 40 | 15.87 |  | 0 | 0 | 0 | 0 | 0 | Survey letter to be issued | Not Approved | 2026-27 |  |  |  | ND
21 | BR. No. 105.8/1731 dated 11.02.16 | 220 kV | LILO of both circuits of 220 kV D/C Gandhinagar TPS - Ranasan line at Bhat substation by using existing RoW of 66 kV Ranasan-Bhat OR 132 kV Ranasan-PRL line | 32 | 39 | 32 | 39 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
22 | BR. No. 105.8/1731 dated 11.02.16 | 220 kV | LILO of both circuits of 220 kV D/C Gandhinagar TPS - Ranasan line at Chiloda substation | 12 | 23.8 | 12 | 23.8 |  | 0 | 0 | 0 | 6 | 9.52 |  | Not Approved | 2023-24 |  |  |  | ND
10 | 95.2/1502 dated 24.06.2014 | 220 kV | 220 kV D/C Bhogat (400 kV) - Moti Gop line | 138.96 | 51.1635 | 136.96 | 9.2835 | 2 | 41.88 | 116.96 | 4.4 | 27.392 | 5.5701 | WIP | 2019-20 | 2022-23 | Spill over | RoW issues | 30 | ND
11 | 105.8/1731 dtd. 11.02.16 | 220 kV | LILO of 220 kV S/C Lalpar - Sartanpar line at 220 kV Wankaner substation on M/C tower by dismentalling of existing 132 kV S/C Lalpar - Wankaner line | 76 | 22.94 | 15 | -0.33 | 61 | 23.27 | 0 | 2.3 | 0 | 0 | WIP | 2018-19 | 2021-22 | Spill over | RoW issues | Stringing | ND
12 | 99.10/1590 | 220 kV | LILO of one circuit of 220 kV D/C Kasor - Gavasad line at 220 kV Gotri substation | 98 | 40.78 | 46 | 20.4 | 52 | 20.38 | 10 | 8 | 9.2 | 12.24 | WIP | 2018-19 | 2022-23 | Spill over | RoW issues | 5 | ND | Line considered in Line length
26 | 99.10/1590 Dt: 09.02.15 | 220 kV | LILO of 220 kV S/C Sartanpar - Wankaner line at 220 kV Makansar substation | 2 | 0.7 | 2 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | Tender to be invited by Field Office | 2021-22 | 2022-23 |  |  |  | ND | Line considered in Line length
27 | 99.10/1590 Dt: 09.02.15 | 220 kV | LILO of 220 kV S/C Morbi - Hadala line at 220 kV Makansar substation | 20 | 8.17 | 20 | 8.17 |  | 0 | 0 | 0 | 0 | 0 |  | 2021-22 | 2023-24 |  |  |  | ND
13 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of both circuits of 220 kV GSEG – Kosamba line at 220 kV Kudiyana with pile foundation | 70 | 45.71 | 70 | 45.71 |  | 0 | 10 | 18.284 | 7 | 4.571 | Survey report received in Jan'2020. Field Office is instructed to carry out SBC for Pile foundation. | 2021-22 | 2024-25 | Spill over | Yet to be awarded |  | ND
29 | 69.6/1071 dated 27.11.10 | 220 kV | LILO of 220 kV S/C Savarkundla - Visavadar at Bagasara s/s | 16 | 2.1275 | 16 | 2.1275 |  | 0 | 0 | 0 | 0 | 0 | - | 2019-20 | 2025-26 |  |  |  | ND
14 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of 220 kV S/C Jetpur - Rajkot line at Metoda s/s (U/G) | 2.6 | 18.75 | 2.6 | 18.73 |  | 0.02 | 0 | 1.875 | 0.52 | 11.238 | Route approval issued (Tender to be invited by S/s Group) | 2019-20 | 2023-24 | Spill over | Yet to be awarded |  | ND
15 | 81.21/1279 dated 04.07.12 and B. R. No. 89.5/1405 dtd. 31.07.13 | 220 kV | LILO of 220 kV S/C Chorania - Sarla & Sarla - Gondal line (due to LILO of 220 kV S/C Chorania - Gondal line at Sarla S/s) at Shapar S/s | 20 | 8.51 | 20 | 8.51 | 0 | 0 | 0 | 0.851 | 4 | 5.106 | Survey under progress | 2019-20 | 2023-24 | Spill over | RoW issues |  | ND
32 | 95.4/1504 dated 24.06.14 (Development of Green Energy Corridor) (Revised as per BR. No. 105.8/1731 dated 11.02.16) | 220 kV | 220 kV Bhogat - Bhatia line | 25.68 | 12 | -0.32 | 2.01 | 26 | 9.99 | 0 | 0 | 0 | 0 | Commissioned on 31.12.2020 | 2019-20 | 2020-21 |  |  |  | ND
16 | 95.4/1504 dated 24.06.14 (Development of Green Energy Corridor) (Revised as per BR. No. 105.8/1731 dated 11.02.16) | 220 kV | 220 kV Bhogat - Ranavav line | 140 | 45.75 | 140 | 13.76 | 0 | 31.99 | 35 | 7 | 28 | 8.256 | WIP | 2019-20 | 2023-24 | Spill over | RoW issues | 34 | ND
17 | 84.11/1325 dated 05.10.12 | 220 kV | 220 kV D/C Pirana (PG) - Barejadi line | 44.96 | 18 | 18.96 | 2.63 | 26 | 15.37 | 0 | 1.2 | 0 | 0 | WIP | 2020-21 | 2021-22 | Spill over | RoW issues |  | ND
18 | 100.8/1606 30.03.2015 | 220 kV | 220 kV D/C Amreli - Babara line | 53 | 21 | 3 | 3.14 | 50 | 17.86 | 0 | 4.2 | 0 | 0 | WIP | 2019-20 | 2021-22 | Spill over | Hotline stringing work awarded on 27.12.21 |  | ND
19 | 100.8/1606 30.03.2015 | 220 kV | 220 kV D/C Babara - Shapar line | 140.98 | 36.6 | 82.98 | 9 | 58 | 27.6 | 0 | 7.05 | 0 | 1.8 | WIP | 2019-20 | 2021-22 | Spill over | RoW issues | Stringing RoW | ND
37 | BR. No. 104.13/1708 dtd. 21.11.15 | 220 kV | 220 kV D/C Wanakbori TPS - Zalod line along with one circuit LILO at Savdasna Muvada | 270 | 98.34 | 270 | 98.34 | 0 | 0 | 0 | 0 | 0 | 0 | NIT to be done | 2021-22 | 2025-26 |  |  |  | ND
20 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of both circuits of 220 kV D/C Otha - Sagapara line at Talaja | 41.08 | 23.29 | 36.62 | 11.2 | 4.46 | 12.09 | 0 | 2.329 | 0 | 2.24 | WIP | 2021-22 | 2021-22 | Spill over | RoW issues |  | GEC-II
39 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Talaja - Maglana line (2 x 60 = 120Ckm) | 120 | 42 | 120 | 42 |  | 0 | 0 | 0 | 12 | 4.2 |  | Not Approved | 2024-25 |  |  |  | GEC-II
40 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Maglana - Pachcham line (2 x 100 = 200Ckm) | 200 | 70 | 200 | 70 |  | 0 | 0 | 0 | 20 | 7 | Survey letter issued on 08.04.2020 | Not Approved | 2024-25 |  |  |  | GEC-II
41 | 69.8/1073 dated 27.11.10 | 220 kV | LILO of 220 kV D/C Ukai (Th) - Achhalia line at 400 kV Achhalia | 20 | 4.27 | 20 | 3.09 |  | 1.18 | 0 | 0 | 0 | 0 | - | 2020-21 | 2026-27 |  |  |  | ND
42 | 69.8/1073 dated 27.11.10 | 220 kV | Termination of 220 kV D/C GPEC - Haldarwa line at Achhalia (400 kV) instead of Haldarwa s/s (Zebra) | 180 | 19.15 | 180 | 19.15 |  | 0 | 0 | 0 | 0 | 0 | - | 2020-21 | 2025-26 |  |  |  | ND
43 | 69.8/1073 dated 27.11.10 | 220 kV | 220 kV D/C Suva - Achhalia (400 kV) line | 140 | 36.23 | 140 | 36.23 |  | 0 | 0 | 0 | 0 | 0 | - | 2020-21 | 2025-26 |  |  |  | ND
44 | 69.8/1073 dated 27.11.10 | 220 kV | 220 kV D/C Prantij - Agiyol ine | 60 | 15.53 | 60 | 15.53 |  | 0 | 0 | 0 | 6 | 1.553 | - | 2020-21 | 2024-25 |  |  |  | ND
45 | 69.8/1073 dated 27.11.10 | 220 kV | 220 kV D/C Prantij - Dhansura line (AP-59) | 70 | 18.11 | 70 | 18.11 |  | 0 | 0 | 0 | 7 | 1.811 | - | 2020-21 | 2024-25 |  |  |  | ND
46 | 100.8/1606 30.03.2015 | 220 kV | 220 kV D/C Babra - Gomta (Gondal-II) | 160 | 65.32 | 160 | 65.32 |  | 0 | 0 | 0 | 16 | 6.532 | - | 2020-21 | 2024-25 |  |  |  | ND
47 | B.R. No. 86.6/1347 dated 04.02.13 130.9/2173 dated 20.08.2020 | 220 kV | LILO of 220 kV S/C Keshod - Timbdi line at 220 kV Veraval | 36 | 15.63 | 36 | 15.63 |  | 0 | 0 | 0 | 0 | 0 | - | 2020-21 | 2025-26 |  |  |  | Scheme Revised
48 | 86.6/1347 dated 04.02.2013 | 220 kV | 220 kV D/C Pipavav - Rajula line | 12 | 6.98 | 12 | 6.98 |  | 0 | 0 | 0 | 0 | 0 | - | 2021-22 | 2025-26 |  |  |  | ND
49 | 86.6/1347 dated 04.02.2013 | 220 kV | LILO of one circuit of 220 kV D/C Chandrapura - Godhara line at 220 kV Halol | 10 | 2.64 | 10 | 2.64 |  | 0 | 0 | 0 | 1 | 0.264 | - | 2020-21 | 2024-25 |  |  |  | ND
50 | 86.6/1347 dated 04.02.2013 | 220 kV | 220 kV D/C Vyankatpura - Halol line | 50 | 13.94 | 50 | 13.94 |  | 0 | 0 | 0 | 0 | 0 | - | 2020-21 | 2025-26 |  |  |  | ND
51 | 99.10/1590 dated 09.02.15 | 220 kV | 220 kV D/C Amreli (400 kV) - Maglana line | 200 | 81.77 | 200 | 81.77 |  | 0 | 0 | 0 | 0 | 0 |  | 2021-22 | 2025-26 |  |  |  | ND
52 | 99.10/1590 dated 09.02.15 | 220 kV | LILO of 220 kV S/C Vallabhipur - Vartej line at 220 kV Maglana substation | 10 | 4.1 | 10 | 4.1 |  | 0 | 0 | 0 | 0 | 0 | Commissioned on 11.11.2020 | 2020-21 | 2020-21 |  |  |  | ND
53 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of both circuit of 220 kV D/C Visavadar - Timbdi line at 400 kV Keshod substation | 24 | 13.42 | 24 | 13.42 |  | 0 | 0 | 0 | 0 | 0 | Keshod land not available | 2021-22 | 2025-26 |  |  |  | GEC-II
54 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220 kV D/C Keshod (400 kV) - Keshod line | 50 | 17.05 | 50 | 17.05 |  | 0 | 0 | 0 | 0 | 0 | Keshod land not available | 2021-22 | 2025-26 |  |  |  | GEC-II
55 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Mansar(Halvad) - Dhama line (2 x 110 = 220Ckm) | 220 | 77 | 220 | 77 |  | 0 | 0 | 0 | 0 | 0 | Dhama land not available | Not Approved | 2026-27 |  |  |  | GEC-II
56 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Dhama - Bechraji line (2 x 45 = 90Ckm) | 220 | 31.5 | 220 | 31.5 |  | 0 | 0 | 0 | 22 | 3.15 | Dhama land not available | Not Approved | 2024-25 |  |  |  | GEC-II
57 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Dhama - Chharodi line (2 x 100 =200Ckm) | 200 | 70 | 200 | 70 |  | 0 | 0 | 0 | 0 | 0 | Dhama land not available | Not Approved | 2025-26 |  |  |  | GEC-II
21 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of 220kV S/C Bala - Dhanki at 220kV Sarla S/s (2 x 45 = 90Ckm) | 90 | 31.5 | 90 | 31.5 |  | 0 | 0 | 3.15 | 45 | 12.6 | Survey letter to be issued by 07.05.20 | Not Approved | 2024-25 | NEW |  |  | GEC-II
22 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of both ckts of 220kV D/C Bhimasar - Charadva at Vankda (Nichimandal), (Shapar) (4 x 10 = 40Ckm) | 8 | 15.81 | 8 | 15.81 | 0 | 0 | 0 | 1.581 | 0 | 0 | WIP | Not Approved | 2022-23 | NEW |  |  | GEC-II | Line considered in Line length
60 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Vankda (Nichimandal) (Shapar) (near Jetpur) - Shapar (400kV) line (2 x 85 = 170Ckm) | 170 | 59.5 | 170 | 59.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2027-28 |  |  |  | GEC-II
61 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of both ckt of 220kV D/C Tappar - Shivlakha line at Shivlakha (400kV) (4 x 25 = 100Ckm) | 100 | 40 | 100 | 40 |  | 0 | 0 | 0 | 4 | 0 | Shivlakha land not available | Not Approved | 2025-26 |  |  |  | GEC-II
62 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of both ckt of 220kV D/C Shapar - Babra at Kamlapur (M/C) (4 x 15 = 60Ckm) | 60 | 23.72 | 60 | 23.72 |  | 0 | 0 | 0 | 30 | 9.488 | 2nd phase | Not Approved | 2023-24 |  |  |  | GEC-II
23 | 129.4/2138 dated 15.06.2020 | 220 kV | LILO of 220 kV S/C Gondal – Padavala – Shapar – Sadla line at 220 kV Kamlapur | 34 | 14.77 | 34 | 14.77 |  | 0 | 34 | 8.862 | 17 | 5.908 | WIP | Not Approved | 2022-23 | NEW |  |  | ND | Line considered in Line length
64 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Kamalpur - Bagodara line (2 x 110 = 220Ckm) | 220 | 77 | 220 | 77 |  | 0 | 0 | 0 | 0 | 0 | Survey letter issued on 08.04.2020 | Not Approved | 2025-26 |  |  |  | GEC-II
65 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Motigop - Gondal II (Gomta) (2 x 125 = 250Ckm) | 250 | 87.5 | 250 | 87.5 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | GEC-II
66 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Ghiyavad - Shapar (400kV) line (2 x 50 = 100Ckm) | 100 | 35.07 | 100 | 35.07 |  | 0 | 0 | 0 | 0 | 0 | Survey done | Not Approved | 2026-27 |  |  |  | GEC-II
24 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of one ckt of 220kV D/C Hadala - Sartanpar at 220kV Ghiyavad (2 x 10 = 20Ckm) | 16 | 7.01 | 16 | 7.01 | 0 | 0 | 4 | 0.701 | 1.6 | 0.701 | WIP | Not Approved | 2022-23 | NEW |  |  | GEC-II | Line considered in Line length
68 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Bagodara - Mogar line (2 x 110 = 220 Ckm) | 220 | 77 | 220 | 77 | 0 | 0 | 0 | 0 | 22 | 7.7 | Survey letter issued on 08.04.2020 | Not Approved | 2024-25 |  |  |  | GEC-II
69 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220kV D/C Gomta - Kamlapur line (2 x 75 = 150Ckm) | 150 | 42.09 | 150 | 42.09 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2025-26 |  |  |  | GEC-II
25 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of both ckts of 220kV D/C Jambuva - Karamsad line at Dhuvaran CCPP (by using existing LILO portion and through 220kV D/C Pachham - Kasor line) | 32 | 64 | 32 | 64 | 0 | 0 | 16 | 6.4 | 16 | 25.6 | Survey letter issued on 08.04.2020 | Not Approved | 2022-23 | NEW |  |  | GEC-II
26 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220 kV D/C Vapi-II (ISTS substation) – Atul (GETCO) line (AL-59 conductor) | 50 | 17.54 | 50 | 17.54 | 0 | 0 | 0 | 1.754 | 25 | 7.016 | Site Selected by PGCIL | Not Approved | 2023-24 | NEW |  |  | ND
72 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of 220 kV S/C Chikhli (Ambetha) – Vapi (GETCO) line at Vapi-II (ISTS substation) (AL-59 conductor) | 40 | 14.03 | 40 | 14.03 | 0 | 0 | 0 | 0 | 20 | 5.612 | Site Selected by PGCIL | Not Approved | 2024-25 |  |  |  | ND
73 | 97.13/1555 dated 20.10.2014 | 220 kV | 220 kV D/C Keshod (400 kV) - Veraval line | 90 | 29.9 | 90 | 29.9 | 0 | 0 | 0 | 0 | 0 | 0 | Survey letter issued in July'18 (Three routes checked) | 2021-22 | 2025-26 |  |  |  | ND
27 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of 220 kV D/C Bhatia - Kalavad line at Khambhalia-II | 54.8 | 10.35 | 54.8 | 10.35 | 0 | 0 | 0 | 1.035 | 0 | 2.07 | WIP | 2021-22 | 2023-24 | Spill over | RoW issues |  | GEC-II
75 | 77.3/1203 dated 16-12-11 and Additional Budget for 40KM approved vide BR no. 95.2/1502 dated 24.06.14 | 220 kV | 220 kV D/C Pipavav - Otha line | 130 | 42.45 | 130 | 42.45 |  | 0 | 0 | 0 | 0 | 0 | - | 2021-22 | 2025-26 |  |  |  | ND
28 | 123.3/2049 dated 22.01.2019 | 220 kV | LILO of one circuit of 220kV D/C Tharad-Deodar at 220kV Mera S/S | 39 | 11.4 | 39 | 11.4 | 0 | 0 | 0 | 2.28 | 15.6 | 6.84 | WIP | Not Approved | 2021-22 | NEW |  |  | KSY
77 | 123.3/2049 dated 22.01.2019 | 220 kV | 220 kV D/C Mera - Agathala line | 70 | 30.4 | 70 | 30.38 |  | 0.02 | 0 | 0 | 35 | 12.152 | Survey report received. Scheme to be dropped. | Not Approved | 2023-24 |  |  |  | ND
78 | 123.3/2049 dated 22.01.2019 | 220 kV | LILO of both circuit of 220kV D/C Kansari-Deodar at 220kV Bhildi | 10 | 34.74 | 1 | 34.74 | 9 | 0 | 0 | 0 | 0.4 | 20.844 | WIP | Not Approved | 2022-23 |  |  |  | KSY
79 | 123.3/2049 dated 22.01.2019 | 220 kV | LILO of both circuit of 220kV D/C Ukai (Hy) - Achhalia line at 220 kV Umarpada (Chikda) | 60 | 52.12 | 60 | 52.12 |  | 0 | 0 | 0 | 0 | 0 | Survey letter issued on 05.03.2019 | Not Approved | 2026-27 |  |  |  | ND
80 | 123.3/2049 dated 22.01.2019 | 220 kV | LILO of one circuit of 220kV D/C Ukai (Hydro) - Umarpada (Chikda) at 220 kV Sarvala with AL-59 conductor (With OPGW) (70 RKM) | 140 | 60.8 | 140 | 60.8 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
81 | 123.3/2049 dated 22.01.2019 | 220 kV | LILO of both of 220kV S/C Anjar - Welspun and 220kV S/C Shivlakha - Welspun at Gandhidham B S/s (2 x 1.5KM, 1200sq. Mm) | 3 | 51.75 | 3 | 51.75 |  | 0 | 0 | 0 | 1.2 | 31.05 |  | Not Approved | 2024-25 |  |  |  | ND
82 | 123.3/2049 dated 22.01.2019 | 220 kV | LILO of both ckt of 220kV S/C Bhimasar - Morbi and 220kV S/C Bhimasar - Sartanpar at Gandhidham B (Padana) S/s (4 x 5 = 20Ckm on M/C towers) | 20 | 10.06 | 20 | 10.06 |  | 0 | 0 | 0 | 2 | 1.006 |  | Not Approved | 2024-25 |  |  |  | ND
83 | 123.3/2049 dated 22.01.2019 | 220 kV | LILO of both ckt of 220kV D/C BECL - Botad line at Avaniya S/s (4 x 15 = 60Ckm on M/C Tower) | 60 | 29.93 | 60 | 29.93 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2025-26 |  |  |  | ND
84 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | LILO of 220kV S/C Mitha - Soja line at 220 kV Mandali | 30 | 10.52 | 30 | 10.52 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2025-26 |  |  |  | ND
85 | B.R No. 119.6/1995 dated 01.06.2018 | 220 kV | 220 kV D/C Chharodi (400 kV) - Mandali line | 120 | 42.09 | 120 | 42.09 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2025-26 |  |  |  | ND
86 | B.R No. 114.6/1908 dated 18.09.2017 | 220 kV | LILO of 220 kV S/C Wanakbori - Asoj & 220 kV S/C Wanakbori - Vyankatpura lines at 220 kV Sevalia substation with M/C tower or 2 X D/C Tower | 22.88 | 31.74 | -0.12 | 0 | 23 | 31.74 | 0 | 0 | 0 | 0 | Commissioned on 11-09-2020 | Not Approved | 2020-21 |  |  |  | ND
87 | B.R No. 114.6/1908 dated 18.09.2017 | 220 kV | LILO of one circuit of 220kV Bhutiya - Agiyol at 220 kV Kheradi | 40 | 14.03 | 40 | 14.03 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
88 | B.R No. 114.6/1908 dated 18.09.2017 | 220 kV | LILO of one circuit of 220kV Agiyol - Dhansura at 220 kV Kheradi | 56 | 19.64 | 56 | 19.64 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
29 | 109.16/1816 dated 27.10.2016 | 220 kV | LILO of bothcircuit of 220kV D/C Tharad-Dhanera at 220kV Rah S/S | 24 | 14.03 | 24 | 14.03 | 0 | 0 | 0 | 5.612 | 9.6 | 8.418 | WIP | Not Approved | 2022-23 | NEW |  |  | KSY | Line considered in Line length
90 | 109.16/1816 dated 27.10.2016 | 220 kV | Up-gradation of 220 kV ACSR Zebra (500 Amp) conductor with high ampacity conductors (around 1000 Amp) (9 nos of lines) | 633.3 | 291.32 | 633.3 | 291.32 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
91 | 129.4/2138 dated 15.06.2020 | 220 kV | LILO of one circuit of 220 kV D/C Ranasan - Karamsad line at Kanbha substation | 2 | 105 | 2 | 105 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2025-26 |  |  |  | ND
92 | 129.4/2138 dated 15.06.2020 | 220 kV | 220 kV Dehgam - Kanbha line | 50 | 23.58 | 50 | 23.58 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2025-26 |  |  |  | ND
93 | 129.4/2138 dated 15.06.2020 | 220 kV | LILO of both circuit of 220 kV D/C Kalavad - Kangashiyali line at Siddheshwar substation | 19 | 25.63 | 19 | 25.63 |  | 0 | 0 | 0 | 1.9 | 2.563 | Survey report received | Not Approved | 2024-25 |  |  |  | ND
94 | 129.4/2138 dated 15.06.2020 | 220 kV | LILO of one circuit of 220 kV D/C Ukai (Th) - Achhalia line (which is not to be LILO at 220 kV Virpore) at 220 kV Balethi substation | 30 | 13.03 | 30 | 13.03 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2025-26 |  |  |  | ND
95 | 129.4/2138 dated 15.06.2020 | 220 kV | 220 kV D/C Kosamba - Balethi line AL – 59 conductor | 70 | 30.4 | 70 | 30.4 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2025-26 |  |  |  | ND
30 | 129.4/2138 dated 15.06.2020 | 220 kV | LILO of 220 kV S/C Kosamba – Ichchhapore line at GSEG along with other miscellaneous work (High Ampacity Conductor) | 16 | 4.6 | 16 | 4.6 |  | 0 | 16 | 4.6 | 0 | 0 | Yet to Award | Not Approved | 2022-23 | NEW |  |  | ND
31 | 129.4/2138 dated 15.06.2020 | 220 kV | LILO of both circuit of 220 kV D/C Palanpur - Kheralu line at 220 kV Sisrana/Satlasana s/s (2x D/C or M/C tower) | 48 | 20.976 | 48 | 20.976 |  | 0 | 10 | 12.5856 | 19.2 | 12.5856 | WIP | Not Approved | 2023-24 | NEW |  |  | KSY
32 | 129.4/2138 dated 15.06.2020 | 220 kV | LILO of 220 kV S/C Jetpur - Visavadar line at 220 kV Bhesan substation | 16 | 6.992 | 16 | 6.992 |  | 0 | 16 | 4.1952 | 6.4 | 4.1952 | WIP | Not Approved | 2022-23 | NEW |  |  | KSY | Line considered in Line length
33 | 129.4/2138 dated 15.06.2020 | 220 kV | 220 kV S/C (400 kV) Jetpur - Bhesan line (Spare S/C line of D/C tower to be used in Jetpur) | 60 | 26.22 | 60 | 26.22 |  | 0 | 0 | 2.622 | 30 | 10.488 | WIP | Not Approved | 2023-24 | NEW |  |  | ND
34 | 129.4/2138 dated 15.06.2020 | 220 kV | 220 kV D/C Bhesan - Patkhilori line AL – 59 conductor | 70 | 30.59 | 70 | 30.59 |  | 0 | 0 | 3.059 | 35 | 12.236 | WIP | Not Approved | 2023-24 | NEW |  |  | ND
35 | 129.4/2138 dated 15.06.2020 | 220 kV | LILO of one circuit of 220 kV Amreli - Babara line at 220 kV Patkhilori | 44 | 34.96 | 44 | 34.96 | 0 | 0 | 44 | 27.968 | 17.6 | 20.976 | WIP | Not Approved | 2022-23 | NEW |  |  | KSY | Line considered in Line length
36 | 129.4/2138 dated 15.06.2020 | 220 kV | 220 kV D/C Patkhilori - Gomta line | 100 | 43.7 | 100 | 43.7 |  | 0 | 0 | 4.37 | 50 | 17.48 | Yet to Award | Not Approved | 2023-24 | NEW |  |  | ND
103 | 130.9/2173 dated 20.08.2020 | 220 kV | LILO of 220 kV S/C Haldarwa - Dahej line and 220 kV S/C Wagra-Dahej line at 400 kV Saykha (Both ckt on M/C Tower) | 4 | 2.09 | 4 | 2.09 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
104 | 130.9/2173 dated 20.08.2020 | 220 kV | 220 kV D/C Saykha-Suva line on M/C Tower | 10 | 10.5 | 10 | 10.5 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
105 | 130.9/2173 dated 20.08.2020 | 220 kV | LILO of 220 kV S/C Ichhapore - Talangpore line at 220 kV Dumas | 11 | 21 | 11 | 21 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
106 | 130.9/2173 dated 20.08.2020 | 220 kV | LILO of 220 kV S/C GSEG - Talanpore line at 220 kV Dumas | 11 | 21 | 11 | 21 |  | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
37 | 130.9/2173 dated 20.08.2020 & 133.4/2218 dated 12.02.2021 | 220 kV | 220 KV D/C Moti Gop - Babarzar substation | 45 | 17.48 | 45 | 17.48 |  | 0 | 10 | 3.496 | 18 | 10.488 | WIP | Not Approved | 2023-24 | NEW |  |  | KSY
108 | 130.8/2172 dated 20.08.2020 | 220 kV | 220 kV D/C Raghanesda - Vav (Khimanvas) with AL-59 Conductor | 35 | 30.64 | 15.3 | -7.5 | 19.7 | 38.14 | 0 | 0 | 0 | 0 | Line charged on 05.07.21 | Not Approved | 2021-22 |  |  |  | ND
109 | 77.3/1203 dated 16-12-11 and Additional Budget for 40KM approved vide BR no. 95.2/1502 dated 24.06.14 | 220 kV | 220 kV D/C Pipavav - Bagasara line | 150 | 48.75 | 150 | 48.75 |  | 0 | 0 | 0 | 0 | 0 | - | 2021-22 | 2026-27 |  |  |  | ND
220 kV Total |  |  |  | 8790.36 | 3610.479 | 8097.47 | 3071.809 | 692.89 | 538.67 | 561.96 | 178.2338 | 678.312 | 361.7069 | [6 empty] | ND
1 | B.R. No. 89.5/1405 dated 31.07.13 | 132 kV | LILO of 132 kV S/C Chhota Udepur - Tilakwada line at220 kV Kawant | 57.72 | 15 | 57.72 | 11.27 | 0 | 3.73 | 30 | 4.5 | 23.088 | 6.762 | WIP | 2022-23 | 2022-23 | NEW |  |  | ND
2 | 95.3/1503 dated 24.06.2014 | 132 kV | LILO of circuit of 132 kV S/C Gondal - Haripur line at 220 kV Visavadar substation | 37.4 | 9.27 | 17.4 | 3.33 | 20 | 5.94 | 0 | 0.6489 | 0 | 0 | WIP | 2017-18 | 2021-22 | Spill over | RoW issues | 1 | ND
3 | BR no. 114.6/1908 dated 18.09.17 | 132 kV | LILO of circuit of 132 kV D/C Mehsana - Patan line at 400 kV Sankhari substation with AL-59 | 50 | 12.88 | 50 | 12.88 | 0 | 0 | 0 | 1.288 | 0 | 2.576 | WIP | 2018-19 | 2022-23 | Spill over | RoW issues | 20 | ND
4 | 95.2/1502 dated 24.06.2014 | 132 kV | 132 kV S/C Sankhari (400 kV) - Deesa line | 40 | 15.7 | 40 | 14.59 | 0 | 1.11 | 5 | 1.57 | 0 | 2.918 | WIP | 2018-19 | 2022-23 | Spill over | RoW issues | 5 | ND
5 | 114.6/1908 dated 18.09.2017 | 132 kV | 132 kV Karamsad - Nadiad line | 10 | 4.67 | 10 | 4.67 | 0 | 0 | 0 | 0 | 4 | 1.868 |  | Not Approved | 2023-24 |  |  |  | ND
5 | 114.6/1908 dated 18.09.2017 | 132 kV | 132 kV Nadiad - Mahemdavad line | 10 | 5 | 10 | 5 | 0 | 0 | 0 | 0.3 | 4 | 2 | Recently awarded | Not Approved | 2023-24 | NEW |  |  | ND
6 | 109.16/1816 dated 27.10.2016 | 132 kV | Up-gradation of 132 kV ACSR Panther (340 Amp) conductor with high ampacity conductors (around 800-1000 Amp) (8 nos of lines) | 291.6 | 100.6 | 291.6 | 100.6 | 0 | 0 | 0 | 5 | 29.16 | 10.06 | Yet to Award | Not Approved | 2025-26 | NEW |  |  | ND
8 | BR no. 107.12/1772 dtd. 20.05.16 | 132 kV | LILO of one circuit of 132 kV D/C Achhalia – Ankleshwar line at Valia substation | 30 | 6.03 | 30 | 6.03 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not Approved | 2026-27 |  |  |  | ND
7 | 105.8/1731 dated 11.02.2016 | 132 kV | LILO of both circuits of 132 kV D/C Shikarpur WF – Samakhiali line at Vondh substation (M/C line with OPGW) | 50 | 18.4 | 50 | 6.17 | 0 | 12.23 | 0 | 1.104 | 0 | 1.234 | WIP | Not Approved | 2021-22 | NEW |  |  | ND
10 | 105.8/1731 dated 11.02.2016 | 132 kV | 132 kV 800 Sq.mm u/g cable from Bhat to Chandkheda by using already available 1.9 Km cable planned for LILO of Ranasan-Sabarmati line at Chandkheda | 10.5 | 28.75 | 10.5 | 19.76 |  | 8.99 | 0 | 0 | 0 | 0 |  | Not Approved | 2027-28 |  |  |  | ND
11 | 105.8/1731 dated 11.02.2016 | 132 kV | 132 kV S/C Samakhiali - Vondh line • Part utilization of old 132 kV Samakhiali - Anjar line, • New 132 kV D/C line from Vondh end (one circuit 66 kV chirai line termination and other circuit 132 kV Samakhiali line termination at Vondh end) | 10 | 2.02 | 10 | 2.02 |  | 0 | 0 | 0 | 4 | 1.212 | Dropped | Not Approved | 2023-24 |  |  |  | ND
12 | 100.8/1606 30.03.2015 | 132 kV | LILO of both circuits of 132 kV D/C Jasdan Wind farm - Jasdan line at 220 kV Babara substation on M/C Tower line (132 kV JASDAN - THIOLIA LINE LILO to 220 kV Babra) | 56.2 | 20 | 46.25 | 5.06 | 9.95 | 14.94 | 0 | 0 | 0 | 1.012 | WIP | 2019-20 | 2021-22 |  |  |  | ND
13 |  | 132 kV | LILO OF 132 KV WANKANER- VARSAMEDI LINE NO.2 AT MOTA DAHISARA WITH ACSR PANTHER CONDUCTOR | 1.97 |  | 1.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WIP |  | 2026-27 |  |  |  | ND
14 |  | 132 kV | LILO OF 132KV S/C RANASAN - VIJAPUR LINE AT 132KV CHILODA S/S WITH ACSR PANTHER CONDUCTOR | 7.816 |  | 7.816 | -0.02 | 0 | 0.02 | 0 | 0 | 0 | 0 | WIP |  | 2026-27 |  |  |  | ND
8 | B.R 131.11/2200 dated 28.10.2020 | 132 kV | 132 kV one ckt of Gondal-Bhayavadhar LILO at Supedi | 4 | 0.74 | 4 | 0.74 |  | 0 | 0 | 0.074 | 0 | 0 | WIP | Not Approved | 2021-22 | NEW |  |  | KSY
Total 132 kV |  |  |  | 667.206 | 239.06 | 637.256 | 192.1 | 29.95 | 46.96 | 35 | 14.4849 | 64.248 | 29.642
Total EHV |  |  |  | 15779.28 | 8764.059 | 13509.59 | 6288.739 | 2269.69 | 2475.32 | 1096.96 | 558.0517 | 1292.459 | 731.6339
66 kV (Lump sum) of Associated Substation | [9 empty] | 644 | 193.2 | 1500 | 650 | [6 empty] | ND
66 kV Lines under KSY | [9 empty] | 1600 | 650 | [8 empty] | KSY
Total 66 kV Lines | [9 empty] | 2244 | 843.2
Total |  |  |  | 15779.28 | 8764.059 | 13509.59 | 6288.739 | 2269.69 | 2475.32 | 3340.96 | 1401.2517 | 2792.459 | 1381.6339
Note on E117: User:2x15 KM 220 kV Cable & 5 KM M/C O/H